## Sheet1
Page	Method	Description	Steps to Test	Observed Result	Expected Result	Tester	Status
Login	Admin Login	Login with the correct user name	Enter correct credentials→Click Login	Takes user to the Systems page	Takes user to the Systems page	DW
Login	Admin Login	Login with the incorrect user name	Enter incorrect credentials→Click Login	Stays at login page	Informs the user of Invalid Credentials	DW	Deficient
Login	Admin Login	Navigate to New Page Without Login	Click Menu→Click Users	Return page: “You must provide a password!” and Java error code	Return page: “You must provide a password!” and Java error code	DW
Database	Test Connection	Test connection with all relevant fields filled correctly	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in with correct info→Click Test Connection	Message:Connected!	Message:Connected!	DW
Database	Test Connection	Test connection with no Username	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and leave the username blank→Click Test Connection	Return page: “Null” and Java error code	Return page: “Null” and Java error code	DW
Database	Test Connection	Test connection with incorrect Username	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and make the username incorrect→Click Test Connection	Return page: “Access denied for user ' username'@'localhost' (using password: YES)” and Java error code	Return page: “Access denied for user ' username'@'localhost' (using password: YES)” and Java error code	DW
Database	Test Connection	Test connection with no password	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and leave the password blank→Click Test Connection	Return page: “You must provide a password!” and Java error code	Return page: “You must provide a password!” and Java error code	DW
Database	Test Connection	Test connection with incorrect password	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and make the password incorrect→Click Test Connection	Return page: “Access denied for user 'root'@'localhost' (using password: YES)” and Java error code	Return page: “Access denied for user 'root'@'localhost' (using password: YES)” and Java error code	DW
Database	Test Connection	Test connection with no Username	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and leave the server blank→Click Test Connection	Return page: “Communications link failure” and Java error code	Return page: “Communications link failure” and Java error code	DW
Database	Test Connection	Test connection with incorrect password	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and make the server incorrect→Click Test Connection	Return page:Communications link failure and Java error code	Return page:Communications link failure and Java error code	DW
Database	Test Connection	Test connection with no Database	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and leave the server blank→Click Test Connection	Message:Connected!	Message:Connected!	DW
Database	Test Connection	Test connection with incorrect Database	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and make the server incorrect→Click Test Connection	Message:Connected!	Message:Connected!	DW
Database	Drop Database	Drop Database with existing database	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in fields and enter existing database→Click Drop Database	Message:Dropped database!	Message:Dropped database!	DW
Database	Drop Database	Drop Database with non-existing database	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in fields and enter existing database→Click Drop Database	Return page: “Can't drop database 'invalid'; database doesn't exist” and Java error code	Return page: “Can't drop database 'invalid'; database doesn't exist” and Java error code	DW
Database	Create Database	Create database with no name	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in fields and leave database blank→Click Create Database	Return page: “Null” and Java error code	Return page: “Null” and Java error code	DW
Database	Create Database	Create new database	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in fields and enter new database→Click Create Database	Message:Created database!	Message:Created database!	DW
Database	Create Database	Create or Drop database with incorrect password	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and make the password incorrect→Click Create/Drop database	Return page: “Access denied for user 'root'@'localhost' (using password: YES)” and Java error code	Return page: “Access denied for user 'root'@'localhost' (using password: YES)” and Java error code	DW
Database	Create Database	Create or Drop database with no password	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field and leave the password blank→Click Create/Drop database	Return page: “You must provide a password!” and Java error code	Return page: “You must provide a password!” and Java error code	DW
Database	Create Database	Create a database that already exist	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in field with existing database→Click Create database	Return page: “Can't create database 'incbootstrap'; database exists” and Java error code	Return page: “Can't create database 'incbootstrap'; database exists” and Java error code	DW
Database	Create Administrator	Create a new administrator	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→ Fill in password field below administrator→Click Create Administrator	Message: Created 'administrator'!	Message: Created 'administrator'!	DW
Database	Create Administrator	Create a new administrator with no password	Enter correct credentials→Click Login→ Click Menu→Click Database Setup→Leave password blank→Click Create Administrator	Return page: “Null” and Java error code	Return page: “Null” and Java error code	DW
Change Password	Change User/Admin Password	Correctly change password	Enter correct credentials→Click Login→ Click Menu→Click Change Password→ Fill in password fields →Click Save	Message: Password changed!	Message: Password changed!	DW
Change Password	Change User/Admin Password	Change password length to shorter than 6 Characters	Enter correct credentials→Click Login→ Click Menu→Click Change Password→ Fill in password fields →Click Save	Return page: “The password must be at least 6 characters in length!” and Java error code	Return page: “The password must be at least 6 characters in length!” and Java error code	DW
Change Password	Change User/Admin Password	Change password to only two of the password categories	Enter correct credentials→Click Login→ Click Menu→Click Change Password→ Fill in password fields →Click Save	Return Page: The password must contain 3 of the following catagories: upper case, lower case, numbers, and symbols!	The password must contain 3 of the following categories: upper case, lower case, numbers, and symbols!	DW	Deficient
Change Password	Change User/Admin Password	Leave Password field empty	Enter correct credentials→Click Login→ Click Menu→Click Change Password→ Fill in password fields →Click Save	Return Page: You must provide a password!	You must provide a password!	DW
Users	add new user	Create a new user	Enter correct credentials→Click Login→ Click Menu→Users→ Click Add →	User Created	User Created	DW
Users	Admin Delegation	As admin, create another admin. Login as New Admin and create user. Try to Login as New User				DW	Deficient
Users	Admin Delegation	As admin, create another admin. Login as New Admin and reset password for a user. Try to Login as Reset User				DW	Deficient
Users	Delete User	Delete a selected User	Enter correct credentials→Click Login→ Click Menu→Users→ Click Delete	User is removed	User is removed	DW
Users	Delete User	Delete a selected User that does not have a SQL name	Enter correct credentials→Click Login→ Click Menu→Users→ Click Delete	User is not removed	User is removed	DW	Deficient
Group List	Add new group	Add a new group to the database	Enter correct credentials→Click Login→ Click Menu→Groups→ Click Add → Mark 'Is Allowed', Display Name, Mark Appropriate members	Return Page: “This need updated so that if a user is added to administrators group, we update the databases user to allow grants!”	New Group created	DW	Deficient
User Edit	Create User	Create a user without display name/SQL User	Enter correct credentials→Click Login→ Click Menu→Users→ Click Add → fill in fields without the display name or SQL User→ Click Save	User is Created	Please enter a Display Name/SQL User	DW	Deficient
Group List	Search Group	Search for groups	Enter correct credentials→Click Login→ Click Menu→Groups→ Type in Search Field → Click Search	List is correctly Sorted based on query	List is correctly Sorted based on query	DW
Securables	Search Securables	Search for Securables	Enter correct credentials→Click Login→ Click Menu→Securables→ Type in Search Field → Click Search	List is correctly Sorted based on query	List is correctly Sorted based on query	DW
Securables	Add Securable	Add new securable to list	Enter correct credentials→Click Login→ Click Menu→Securables→ Click Add	Return Page: The requested securable could not be found!	Take user to the Securable Edit List	DW	Deficient
Computer List	Add Computer	Add a new Computer to list	Enter correct credentials→Click Login→ Click Menu→computers→ Click Add	Take user to the computer edit page	Take user to the computer edit page	DW
Computer List	Search Computers	Search for Computers	Enter correct credentials→Click Login→ Click Menu→Computers→ Type in Search Field → Click Search	List is correctly Sorted based on query	List is correctly Sorted based on query	DW
Computer List	Delete Computer	Delete a selected computer	Enter correct credentials→Click Login→ Click Menu→computers→ Click delete	Removes computer from list	Removes computer from list	DW
Computer Edit	Save Computer	Save Computer with all fields filled in correctly	Enter correct credentials→Click Login→ Click Menu→computers→ Click Add→ Fill in Description, Fill in MAC Address, mark “Is Allowed”→ Click Save	New Computer is properly added	New Computer is properly added	DW
Computer Edit	On Load	Have “Is Allowed” marked by default	Enter correct credentials→Click Login→ Click Menu→computers→ Click Add	“Is Allowed” is not marked by default	“Is Allowed” marked by default	DW	Deficient
Computer Edit	Save Computer	Save Computer with all fields being left blank	Enter correct credentials→Click Login→ Click Menu→computers→ Click Add→ do no fill in any fields→ Click Save	New blank Computer is added	Message: Please fill in specified fields!	DW	Deficient
Computer Edit	Save Computer	Save Computer with duplicate Description/Mac Address	Enter correct credentials→Click Login→ Click Menu→computers→ Click Add→ Create Duplicate entry→ Click Save	Message: Duplicate entry” for key ' MAC Address/Description'	Message: Duplicate entry for key ' MAC Address/Description'	DW	Deficient
User Edit	Save User	Save User with duplicate Display Name	Enter correct credentials→Click Login→ Click Menu→Users→ Click Add→ Create Duplicate entry→ Click Save	Message: Duplicate entry” for key 'Display Name'	Message: Duplicate entry for key ' Display Name'	DW	Deficient
Settings List	Search Settings	Search the Settings list	Enter correct credentials→Click Login→ Click Menu→Settings→ Type in Search Field → Click Search	List is correctly Sorted based on query	List is correctly Sorted based on query	DW
Settings List	Add Settings	Add a new Setting to list	Enter correct credentials→Click Login→ Click Menu→Settings→ Click Add	Takes user to the Settings Edit page	Takes user to the Settings Edit page	DW
Settings List	Delete Settings	Delete a selected Settings	Enter correct credentials→Click Login→ Click Menu→Settings→ Click delete	Deletes selected Setting	Deletes selected Setting	DW
Setting Edit	Save Setting	Save New Setting with all field filled in correctly	Enter correct credentials→Click Login→ Click Menu→Settings→ Click Add→ Fill in all appropriate fields→ Click Save	Setting Saves Correctly	Setting Saves Correctly	DW
Setting Edit	Save Setting	Save New Setting with all fields blank	Enter correct credentials→Click Login→ Click Menu→Settings→ Click Add→ Leave fields blank→ Click Save	Setting Saves	Message: Please fill in specified fields!	DW	Deficient
Setting Edit	Save Setting	Save Duplicate Setting	Enter correct credentials→Click Login→ Click Menu→Settings→ Click Add→ Fill in all appropriate fields→ Click Save	Setting Saves	Message: This Settings already exists!	DW	Deficient
Log List	On Load	List is not showing the SQL User	Enter correct credentials→Click Login→ Click Menu→Logs	List is not showing the SQL User	The SQL User needs to be shown	DW	Deficient
Log List	Add Log	Manually add a new log	Enter correct credentials→Click Login→ Click Menu→Logs→Add	Return Page: The log entry requested could not be found!	Return Page: The log entry requested could not be found!	DW
Log List	Delete Log	Delete a selected log	Enter correct credentials→Click Login→ Click Menu→Logs→Delete	Return Page: You may not delete log entries!	Return Page: You may not delete log entries!	DW
Report List	Search Report	Search the Report list	Enter correct credentials→Click Login→ Click Menu→Report→ Type in Search Field → Click Search	List is correctly Sorted based on query	List is correctly Sorted based on query	DW
Report List	Add Report	Add a new Report to list	Enter correct credentials→Click Login→ Click Menu→Report→ Click Add	Takes user to the Report Edit page	Takes user to the Report Edit page	DW
Report List	Delete Report	Delete a selected Report	Enter correct credentials→Click Login→ Click Menu→Report→ Click delete	Return Page: Cannot delete or update a parent row: a foreign key constraint fails ("incbootstrap"."report blocks", CONSTRAINT "Blocks>Report" FOREIGN KEY ("Reports GUID") REFERENCES "reports" ("GUID"))	Deletes selected Setting	DW	Deficient
Report Edit	Save Report	Save New Report with all field filled in correctly	Enter correct credentials→Click Login→ Click Menu→Report→ Click Add→ Fill in all appropriate fields→ Click Save→ Click Save	Report Saves Correctly	Setting Saves Correctly	DW
Report Edit	Save Report	Save New Report with all fields blank	Enter correct credentials→Click Login→ Click Menu→Report→ Click Add→ Leave fields blank→ Click Save→ Click Save	Report Saves	Message: Please fill in specified fields!	DW	Deficient
Report Edit	Save Report	Save Duplicate Report	Enter correct credentials→Click Login→ Click Menu→Report→ Click Add→ Duplicate all appropriate fields→ Click Save	Message: Duplicate entry 'Report - null' for key 'Display Name' and the program breaks	Message: Duplicate entry 'Report - null' for key 'Display Name'	DW	Deficient
All Lists	Is Allowed	“Is Allowed” needs to be added to all foreign key lists	Enter correct credentials→Click Login→ Click Menu→Desired Category	“Is allowed” is missing from securables	“Is Allowed” needs to be added to all foreign key lists	DW	Deficient
All Edit pages	Edit Save	On Save, bring user to record just saved, or return to list	Enter correct credentials→Click Login→ Click Menu→Click Desired Item→ Click Add→ Fill in all appropriate fields→ Click Save→	Remains on Edit Screen	On Save, bring user to record just saved, or return to list	DW	Deficient